## Sheet1
Bug_162	27-12-2018	Hospital detail page -> Professionals	Docter should not allow to book an appointment	If any other docter is viewing hospital detail page then it should not allowing to book an appointment	Major	Done	No
Bug_164	28-12-2018	Manage Appointments -> HCP	button is not displaying properly	It is displaying reject and cancel button togather	Major	Open	Yes	Appoint_hcp.png
Bug_160(1)	28-12-2018	Manage Appointments -> HCP	It should display clear filter option	Same issue in Manage Appointments -> Patient	Suggestion	Open	No
Bug_214	03-01-2019	Notification -> HCP	Notification is missing	When patient sent request for book appointment then it should notify to HCP	Major	Open	No
Bug_219	03-01-2019	Appointment request list -> Patient	Filter is not working		Critical	Open	No
Bug_237	03-01-2019	Patient profile page -> professionals -> HCP	Book and appointment button is displaying	If HCP is viewing Professional tab then it should not display "Book an appointment" button / Same issue in Hospital detail page,department detail page	Major	Open	No
Bug_263	08-01-2019	Appointment request -> HCP	Not displaying request	If user book an appointment then request is not displaying to Docter	Critical	Open	No